P384 Review

Lead Monitor Guidelines

| Prior to the review |  |  | Day of the review | Following the review |
| --- | --- | --- | --- | --- |
| 60 – 45 days | 45 – 30 days | 14 – 7 days |  | 30 – 60 days |
| - Contact agency - notify of review date -or- negotiate alternate date - Contact IPI - coordinate with Medicaid review - Contact Licensing - coordinate with annual review - Select team members with RPM Mgr. | - Send letter to agency - see form letter - confirm review date - request QA information - Select, notify peer - agency chooses 3 from peer list - monitor, RPM Mgr pick 1 of 3 - if no peer response in 3 days, select another - Notify team members - date/time of review, assignments - notify RPM Mgr. if member unavailable | - QA Mgr receives QA information from agency - Clarify expectations with agency - adequate space for file reviews - agency coverage for staff during interviews - private space for interviews - Email reminder to team - give review date, time, directions, other relevant information - Obtain UIR information from QA - Select youth for review - 15% of all youth, or minimum of 4 - Develop schedule for day of review - Copy documents for team members for day of review - P384 - P384 file review tool - P384 questionnaires for clients, direct service staff | - Finalize review day schedule - identify scheduled staff for interviews - notify agency of youth for review (NOTE: no youth to be removed from school) - Facilitate introductory meeting - keep it brief! - introduce participants - distribute review schedule - answer agency questions - Receive file orientation - keep it brief! - Receive facility tour - keep it brief! - Complete file reviews/interviews - Process preliminary findings with team members - Present preliminary findings to agency administration - Lead Monitor, RPM Mgr., QA Mgr. only | - Complete draft review report with recommendations - send draft interview section to interviewers (give 1 week for feedback) - send draft file review section to file reviewers (give 1 week for feedback) - send draft report to L. Karfs by 30th day after review - QA completes draft QA portion of review report with recommendations - Review draft reports with L. Karfs, QA Mgr. - Consolidate QA portion into overall report - L. Karfs approves, forwards completed P384 report to N. Brown and agency |