P384 Review

Lead Monitor Guidelines

| Prior to the review | Day of the review | Following the review |
| --- | --- | --- |
| 60 – 45 days | 45 – 30 days | 14 – 7 days |  | 30 – 60 days |
| Contact agency notify of review date -or- negotiate alternate date Contact IPI coordinate with Medicaid review Contact Licensing coordinate with annual review Select team members with RPM Mgr. | Send letter to agency see form letter confirm review date request QA information Select, notify peer agency chooses 3 from peer list monitor, RPM Mgr pick 1 of 3 if no peer response in 3 days, select another Notify team members date/time of review, assignments notify RPM Mgr. if member unavailable | QA Mgr receives QA information from agency Clarify expectations with agency adequate space for file reviews agency coverage for staff during interviews private space for interviews Email reminder to team give review date, time, directions, other relevant information Obtain UIR information from QA Select youth for review 15% of all youth, or minimum of 4 Develop schedule for day of review Copy documents for team members for day of review P384 P384 file review tool P384 questionnaires for clients, direct service staff | Finalize review day schedule identify scheduled staff for interviews notify agency of youth for review (NOTE: no youth to be removed from school) Facilitate introductory meeting keep it brief! introduce participants distribute review schedule answer agency questions Receive file orientation keep it brief! Receive facility tour keep it brief! Complete file reviews/interviews Process preliminary findings with team members Present preliminary findings to agency administration Lead Monitor, RPM Mgr., QA Mgr. only | Complete draft review report with recommendations send draft interview section to interviewers (give 1 week for feedback) send draft file review section to file reviewers (give 1 week for feedback) send draft report to L. Karfs by 30th day after review QA completes draft QA portion of review report with recommendations Review draft reports with L. Karfs, QA Mgr. Consolidate QA portion into overall report L. Karfs approves, forwards completed P384 report to N. Brown and agency |